## Dashboard
Smart Consumer Metering Status as on 20-Aug-2026
Latest official all-India figure: 7.24 crore (72.4 mn) meters installed as of 30-Jun-2026 (MoS Power reply in Parliament, 06-Aug-2026). Blue = hardcoded from source; yellow = estimate/derived. See 'Sources & Notes' sheet.
Smart meters execution tracker (half-yearly)
Period | Cumulative installed, mn (period end) | Installed in period, mn | Growth %
2HCY24 | 18 | - | -
1HCY25 | 27.7 | 9.7 | 53.89%
2HCY25 | 49.3 | 21.6 | 77.98%
1HCY26 | 72.4 | 23.1 | 46.86%
Run-rate: ~1.35 lakh meters/day (Feb-2026); implied ~79 mn installed by 20-Aug-2026 (est.)
India summary — all schemes (RDSS + NSGM/others)
India | Unit | Sanctioned | Awarded | Deployed | To be awarded
Smart meters | Mn Nos | 222 | 156 | 72.4 | 66
Approximate Realisation | Rs./unit | 11000 | 11000 | 11000 | 11000
Total Opportunity | Rs. Mn | 2442000 | 1716000 | 796400 | 726000
Awarded % of sanctioned | % | 70.27%
Deployed % of sanctioned | % | 32.61%
Smart Meter Mission split, mn meters (Total =D14= 222 mn)
Category | Mn meters | % of total
Awarded & Installed | 72.4 | 32.61%
Awarded, Not yet Installed | 83.6 | 37.66%
Not Yet Awarded | 66 | 29.73%
Total | 222 | 100%
RDSS scheme detail (sanctioned 20.33 crore; sunset 31-Mar-2028)
RDSS component | Sanctioned, mn | Installed, mn | As of
Consumer smart meters | 197.9
DT meters | 5.253
Feeder meters | 0.205
RDSS total | 203.358 | 57.3 | 30-Jun-26
Other schemes (NSGM etc.) |  | 15.1 | 30-Jun-26
Prepaid mode (of installed) |  | 16 | 11-Dec-25
State-wise Smart Meters, mn nos (sanctioned per RDSS approvals; installed = latest reported)
State | Sanctioned | Installed | Installed as of | % Installed | Remark
Uttar Pradesh | 31 | 6.5 | Nov-25 | 20.97% | Awarded ~ full sanction
Tamil Nadu | 30 | 0.1 | Nov-25 | 0.3333% | Tenders still not finalised; rollout yet to start
Maharashtra | 24 | 7.4 | Nov-25 | 30.83% | No.2 in installations; leads DT metering
West Bengal | 21 | n/a |  | n/a | Largely yet to be awarded
Bihar | 17.2 | 8.2 | Nov-25 | 47.67% | No.1 in installations; 100% prepaid
Gujarat | 17 | n/a |  | n/a
Rajasthan | 15 | n/a |  | n/a
Madhya Pradesh | 13 | 1 | Dec-24 | 7.692%
Kerala | 13 | 0 |  | 0% | Not awarded (KSEB opposition to AMISP/TOTEX)
Punjab | 10 | n/a |  | n/a
Assam | 3.3 | 3.3 | Mar-25 | 100% | Fastest % completion; ~80% rural
Haryana | 1 | n/a |  | n/a
Top-12 total | 195.5 | 26.5
AMISP / EPC players — order books & installations (mid-2026)
Player | Order book, mn meters | Order book value, Rs. bn | Installed till date, mn | As of / note
Genus Power (incl. SPVs/GIC JV) | 36.1 | 251.7 | 10 | Per Q4FY26 call transcript (19-May-26): order book Rs.25,173 cr incl. SPVs/GIC platform; 24 AMISP projects all OGL, awarded base 3.61 cr meters; crossed 1 cr installed under RDSS (Q&A: 87 lakh own-RDSS, ~30 lakh in Q4); targets >1 cr installs & Rs.6,000-6,500 cr revenue in FY27; capacity 1.8 cr meters/yr
Adani Energy Solutions (AESL) | 24.6 | 295.2 | 13.4 | Rev. potential Rs.29,519 cr; first to 1 crore delivered (Feb-26); 13.4 mn = ~55% of mandate (Jun-26)
GMR Smart Electricity | 7.6 | 76 | n/a | No 2026 update found; shortlisted bidder for IntelliSmart (~$400 mn sale)
L&T | 5.2 | 61.8 | n/a | No 2026 update found
Techno Electric | - | - | n/a | Targets completing RDSS smart metering mandates by Dec-2026
IntelliSmart (NIIF-EESL JV) | - | - | n/a | Stake sale in progress (~$400 mn); Adani & GMR final bidders
Key meter manufacturers: Genus Power, Secure Meters, HPL Electric, Schneider Electric, Polaris Smart Metering

## Statewise S-A-I
State/UT-wise Smart Meters under RDSS — Sanctioned / Awarded / Installed
Official source: Rajya Sabha Unstarred Question reply, 10-Feb-2025 (Ministry of Power), via data.gov.in API (resource da474c10-b5dc-4e65-b5af-7687ac3079f1). RDSS meters only (consumer + DT + feeder) — Bihar's large pre-RDSS/state-scheme rollout and Haryana/Karnataka/Telangana/Odisha (no RDSS metering sanction) are outside this table. 'Latest installed' column = newer all-scheme press figures where available (dates noted).
State/UT | Sanctioned | Awarded | Installed | Awarded % | Installed % | Latest installed (mn, all schemes) | As of
Tamil Nadu | 30490774 | 0 | 0 | 0% | 0%
Uttar Pradesh | 28526731 | 28526730 | 858147 | 100% | 3.008% | 6.51 | 15-Nov-25
Maharashtra | 24004866 | 25273775 | 696405 | 105.3% | 2.901% | 7.4 | 15-Nov-25
West Bengal | 21035262 | 4031566 | 178681 | 19.17% | 0.8494%
Gujarat | 16787587 | 11071687 | 425818 | 65.95% | 2.537%
Rajasthan | 14736692 | 14754023 | 11416 | 100.1% | 0.07747%
Madhya Pradesh | 13429206 | 5490509 | 1366302 | 40.88% | 10.17% | 1.01 | 02-Dec-24
Kerala | 13383001 | 291690 | 0 | 2.18% | 0%
Punjab | 8981414 | 0 | 0 | 0% | 0%
Assam | 6445127 | 6558446 | 2520475 | 101.8% | 39.11% | 3.28 | 18-Mar-25
Chhattisgarh | 6179479 | 7345604 | 1046898 | 118.9% | 16.94%
Andhra Pradesh | 5919344 | 5981561 | 823382 | 101.1% | 13.91%
Himachal Pradesh | 2841908 | 934409 | 103524 | 32.88% | 3.643%
Bihar | 2607153 | 2598542 | 1861464 | 99.67% | 71.4% | 8.24 | 15-Nov-25
Uttarakhand | 1649684 | 1649684 | 12720 | 100% | 0.7711%
Jammu and Kashmir | 1497690 | 1490727 | 14707 | 99.54% | 0.982%
Jharkhand | 1362044 | 1362044 | 15680 | 100% | 1.151%
Goa | 750356 | 0 | 0 | 0% | 0%
Tripura | 562870 | 427013 | 3694 | 75.86% | 0.6563%
Meghalaya | 472743 | 0 | 0 | 0% | 0%
Puducherry | 407052 | 0 | 0 | 0% | 0%
Nagaland | 323878 | 323878 | 0 | 100% | 0%
Arunachal Pradesh | 298250 | 298250 | 276 | 100% | 0.09254%
Mizoram | 292081 | 292081 | 0 | 100% | 0%
Manipur | 166208 | 166208 | 628 | 100% | 0.3778%
Sikkim | 148542 | 148542 | 11170 | 100% | 7.52%
Andaman and Nicobar Islands | 84835 | 0 | 0 | 0% | 0%
Delhi | 3521 | 0 | 0 | 0% | 0%
Total (sum of states) | 203388298 | 119016969 | 9951387 | 58.52% | 4.893%
All India Total (as printed in reply) | 203388298 | 119016969 | 9951387
Later all-India milestones for context: installed 49.3 mn (11-Dec-25, Minister), 72.4 mn total / 57.3 mn RDSS (30-Jun-26, Parliament); awarded/tendered ~156 mn (Genus Q4FY26 call, 19-May-26).

## Sources & Notes
Item | Detail
All-India installed 72.4 mn (30-Jun-26) | MoS Power Shripad Naik, written reply in Parliament, 06-Aug-2026 — 7.24 crore total (5.73 crore under RDSS). tndindia.com/indias-smart-meter-population-at-7-24-crore-parliament
RDSS sanction 20.33 crore | Same reply: 19.79 crore consumer + 52.53 lakh DT + 2.05 lakh feeder; RDSS sunset 31-Mar-2028
Cumulative milestones | Nov-24: 16.8 mn (NSGM); Mar-25: 24.0 mn (NSGM via tndindia); mid-25: ~27.7 mn (indiasmartgrid.org); 15-Nov-25: 47.6 mn (Mercom India); 11-Dec-25: 49.3 mn, 1.6 cr prepaid (Power Minister, newsonair.gov.in); 15-Feb-26: 58.3 mn @ ~1.35 lakh/day (PFI/pfie.com); 30-Jun-26: 72.4 mn (Parliament)
Awarded 156 mn (15.6 crore) | PRIMARY SOURCE: Genus Power Q4FY26 earnings call transcript, 19-May-2026 (BSE/NSE filing, provided by user) — prepared remarks: 'only around 15.6 crore meters have so far been tendered'; Q&A: '15 crores has already been tendered and 7 crores has been installed', with a further ~5 crore of tenders live (Haryana/MP/Punjab/TN) and 9 crore expected in FY27. Trajectory check: NSGM dashboard showed 13,80,22,912 (138.02 mn) awarded of 22,23,54,490 sanctioned in early 2025; CareEdge: 10.9 crore awarded Mar-2024.
State installed figures | Bihar 8.24 mn, Maharashtra 7.40 mn, UP 6.51 mn as of 15-Nov-25 (Mercom India). Assam 3.28 mn (Mar-25, tndindia). MP 1.01 mn (Dec-24, Rajya Sabha). Tamil Nadu & Kerala: rollout not started (tender delays / AMISP opposition). Blank = no recent public figure.
State sanctioned figures | Carried from RDSS approvals (unchanged — Prayas: no fresh sanctions in FY25). Bihar shown at 17.2 (172.09 lakh, tndindia Mar-25).
Genus Power | Order book ~Rs.24,020 cr incl. SPVs & GIC platform (Jun-26 / Q4FY26 call); ~2.75 crore meters (BusinessToday Apr-26); 1 crore installed under RDSS across 9 states (Feb-26, Energetica India); targets 1 crore installs in FY27; capacity 1.8 crore/yr
Adani Energy Solutions | Order book 24.6 mn meters, revenue potential Rs.29,519 cr; 13.4 mn installed by Q1 FY27 (~55% of mandate) (Whalesbook/company); first to deliver 1 crore meters 05-Feb-26 (adani.com)
GMR / L&T | No 2026 public update found — figures carried from your 04-Mar-25 sheet. GMR & Adani are final bidders for IntelliSmart (~$400 mn, BW Businessworld)
Target / deadline | RDSS target 25 crore prepaid smart meters; original Mar-2026 deadline extended ~2 years (sunset 31-Mar-2028)
Realisation Rs.11,000/unit | Assumption carried from your original sheet. Prayas Mar-25: single-phase award rates Rs.7,236–12,118/unit, median Rs.8,839
Access note | nsgm.gov.in / pib.gov.in are geo-blocked from this environment (connection reset) — figures compiled from Parliament replies and industry press instead of the live NSGM dashboard.

## Genus Q4FY26 Call
Genus Power Q4 & FY26 Earnings Call — 19-May-2026 (transcript filed 26-May-2026). Source: user-provided PDF (BSE/NSE filing).
Item | Figure | Detail
Industry: total consumer base | 31-32 crore | To be replaced with smart meters over next 4-5 years (JMD, Q&A)
Industry: tendered so far | 15.6 crore | Prepared remarks: 'only around 15.6 crore meters have so far been tendered'; Q&A rounds to 15 crore
Industry: installed | 7 crore | Matches official 7.24 crore as of 30-Jun-26
Industry: remaining to install | 24-25 crore
Industry: RDSS sanctioned | 23 crore | Program extended till 2028
Tenders live now | ~5 crore | Haryana, MP, Punjab, Tamil Nadu
Tender pipeline | 4+ crore | More Haryana, Punjab, Delhi; large quantities from West Bengal, Kerala
Tenders expected in FY27 | 9 crore
Q4FY26 revenue (standalone) | Rs.1,524 cr | +63% YoY, +36% QoQ
Q4FY26 EBITDA / PAT | Rs.284 cr / Rs.181 cr | +36% / +41% YoY
FY26 revenue | Rs.4,738 cr | +94% YoY
FY26 EBITDA | Rs.960 cr | +104% YoY; margin 20.3% (+102 bps)
FY26 PAT | Rs.605 cr | +106% YoY; margin 12.8%
Order book (31-Mar-26) | Rs.25,173 cr | Net of taxes, incl. all SPVs & GIC platform; concessions 8-9 yrs
Order book split | 23,000 + 2,000 | Rs.23,000 cr platform (Rs.16,000 cr capex + ~Rs.7,000 cr opex/O&M); Rs.2,000 cr exports/gas/water/other AMISPs/utilities
AMISP projects / awarded base | 24 / 3.61 crore | All 24 projects Operational-Go-Live
Meters installed under RDSS | 1 crore+ crossed | Q&A: 87 lakh under RDSS program; ~30 lakh installed in Q4FY26
Manufacturing capacity | >1.8 crore/yr | 'exceeding 18 million meters annually'
Market share | 22-23% / >30% | As AMISP / as meter manufacturer + AMISP
FY27 guidance: revenue | Rs.6,000-6,500 cr
FY27 guidance: EBITDA margin | ~18% | -2.5pp: RM/chips/forex; fixed-price contracts, no pass-through; hardware ~45-50% of platform book
FY27 guidance: installs | >1 crore meters
FY27 capex | Rs.10-20 cr | Routine only (dies & molds)
O&M revenue | Rs.150 cr -> Rs.800-900 cr/yr | FY26 -> within 2-3 yrs, sustained 5-7 yrs, on current order book
Net debt | Rs.1,573 cr | vs Rs.605 cr Mar-25; peak expected Rs.1,900-2,000 cr
Cash & equivalents | Rs.719 cr | FDs & current investments
GIC platform (Gemstar) investment | Rs.487 cr done | Genus 26% / GIC 74%; further Rs.600-700 cr over FY27-Q1FY29
Working capital days | 343 -> 274 | Debtors 187->89, inventory 127->104; another 50-75 day cut expected FY27
Cash flow outlook | Positive from FY28 | ~Breakeven/slightly negative by end-FY27; positive from Q1-Q2 FY28
Gas meters opportunity | 12 crore / Rs.35,000-36,000 cr | Mandated over 3-4 yrs; Genus to participate
Exports target | Rs.500 cr in 2-3 yrs | Australia go-live expected in 3-6 months
R&D team | ~300 device + ~250 software | HES/MDM/WFM in-house; proprietary interoperable RF mesh
IntelliSmart bid | No comment | Decision rests with GIC as platform majority owner

## Bidding Intensity
AMISP Bidding — Competitive Intensity Data
Note: L1 vs L2 financial bid spreads are NOT public — RFP & AMISP contracts carry confidentiality clauses (Prayas, Apr-2025). Competitive intensity must be read from: (1) award-rate dispersion, (2) PMPM service-charge spread, (3) bidder pools per tender, (4) benchmark-vs-L1 gaps, (5) consolidation.
1) Award-rate dispersion — single-phase consumer meters, 33 discoms (RDSS dashboard via Prayas, Apr-2025)
Metric | Rs./meter (10-yr TOTEX)
Lowest award rate | 7236
Median | 8839
Mean (right-skewed) | 9093
Highest (large discoms) | 12118
Outlier: Sikkim (smallest volume) | 14697
Max/Min spread | 1.67x
DT meters: Rs.15,962 - 51,660 (median 28,954). Feeder: Rs.14,755 - 1,33,765 (median 48,529; Tripura/Mizoram/HP highest). Select-state single-phase: highest exceeds lowest by 45%, no correlation with volume.
2) PMPM service charge won (= (award rate - subsidy)/93 months) — proxy for how aggressively each state's tender was bid
State | PMPM Rs./meter/month
West Bengal (lowest = most aggressive) | 60
Rajasthan | 79
Madhya Pradesh (avg, highest) | 146
MP Paschim discom (max) | 167
Spread | 2.8x
3) Tender case studies — bidder pools & outcomes
Tender | Size | Bidders / competition | Outcome
UP 4 discoms, Round 1 (2022) | 2.85 cr meters, ~Rs.23,000 cr | Adani, GMR, L&T bid all 4; IntelliSmart 2 (3-4 bidders/tender) | Scrapped: L1 (Adani) quoted ~Rs.10,000/meter vs REC benchmark ~Rs.6,000 — 67% above benchmark
UP re-bid (2023) | Same | Same pool | PVVNL: IntelliSmart L1 (67 lakh, Apr-23); awards near Rs.9,000/meter level (national median 8,839)
MSEDCL Maharashtra (Sep-23) | 6 packages, 1.72+ cr meters, Rs.20,000+ cr | Multiple packages split competition | Winners: Adani (largest share), NCC, Genus, Montecarlo
Chhattisgarh Pkg-2 (2023) | ~Rs.1,744 cr / 10 yrs | n/a | Tata Power L1
Tamil Nadu R1 (2025) | 82 lakh meters, ~Rs.19,000 cr | n/a | Cancelled (Adani-linked controversy); re-tendered via PFC Consulting
Tamil Nadu Phase-2 (Jun-26) | 5.45 lakh meters | Restricted to 8 empanelled Group-2 entities: Apraava, Adani, Genus, IntelliSmart, GMR, Iskraemeco, Polaris, Montecarlo | Bidding ongoing; R1 closed 16-Mar-26
Punjab PSPCL (Jan-26) | ~1 cr meters | PSU route | TCIL L1 (LoA 30-Jan-26); agreement unsigned as of Jul-26 amid CAPEX-vs-RDSS dispute (~Rs.350 cr implication alleged)
4) Market structure & consolidation
- AMISP market shares (Genus mgmt, Q4FY26 call): Genus ~22-23% as AMISP, >30% as manufacturer+AMISP; AESL order book 24.6 mn meters; IntelliSmart ~Rs.20,000 cr orders (UP/Gujarat/Bihar/Assam); AESL ~Rs.25,000 cr (Maharashtra/Bihar/Assam/AP).
- Manufacturing: ~10 crore meters/yr capacity; top 8-9 manufacturers hold 70-80% (CareEdge, Mar-25). Genus alone 1.8 crore/yr.
- Consolidation shrinking the bidder pool: IntelliSmart stake sale (~$400 mn; Adani & GMR in final round); Polaris Smart Metering sale (Adani, Actis, Apraava in round 2).
- Barriers to entry keep intensity moderate: TOTEX annuity over 93-month O&M, DDF payment security, working-capital drag (Genus WC 274 days FY26), empanelment requirements.
- Trend: FY27 pipeline of ~9 crore meters of tenders (Genus call) vs 8-10 active AMISPs -> intensity rising in large states, single-bidder risk persists in small/NE states.
Sources: Prayas (Energy Group) Apr-2025 (RDSS dashboard compilation); ThePrint 24-Oct-22; T&D India 22-Sep-23 & 15-Jun-26; Tehelka Jul-26; CareEdge Mar-2025; Genus Q4FY26 call transcript; Tata Power release.