## README
India distributed solar: rooftop households (PM Surya Ghar) and solar pumps (PM-KUSUM) - annual additions and current targets
Scheme: PM Surya Ghar: Muft Bijli Yojana (PMSG:MBY), Ministry of New & Renewable Energy (MNRE). Launched 13 Feb 2024, Cabinet approved 29 Feb 2024, outlay Rs 75,021 crore.
Compiled 1 Oct 2026 from Parliament answers (Lok Sabha / Rajya Sabha), PIB press releases, MNRE, PRS and the scheme's National Portal. Every number carries its source and 'as on' date in the Timeline sheet.
CURRENT TARGET (official, unchanged since Feb 2024): 1 crore (10 million) residential households with rooftop solar by FY 2026-27, i.e. by 31 March 2027. Reaffirmed in Lok Sabha Starred Q.59 answered 22 Jul 2026.
Interim target stated by Minister Pralhad Joshi (PIB, 4 Jun 2026): 75 lakh households by December 2026. Annual target for FY 2025-26 (Rajya Sabha, 8 Dec 2025): 35 lakh households. MNRE Secretary (press, 15 Sep 2026): likely 85-90 lakh by March 2027, i.e. a shortfall vs 1 crore.
HOW TO READ 'ANNUAL ADDITIONS': MNRE does not publish a financial-year-wise series of households added. It publishes cumulative figures with an 'as on' date. The Annual_Additions sheet derives yearly additions as the difference between the nearest official cumulative datapoints to each year-end. Yellow cells are derived/approximate; the anchor dates are shown so you can judge the gap to the actual year-end.
TWO COUNTS: 'RTS systems installed' (one rooftop plant) vs 'households benefitted' (a group-housing-society plant counts many households). Official statements switch between the two; the 'target' is in households. Both are tracked here.
PRE-SCHEME BASELINE: 7.94 lakh residential rooftop installations in the entire decade before Feb 2024 (MNRE, Aug 2026), i.e. roughly 7,000 per month (Minister Joshi, Jun 2026). PM Surya Ghar is now running at 3-5 lakh per month.
Sheets: Annual_Additions ¦ Timeline (all official datapoints) ¦ Targets ¦ Monthly_RunRate ¦ State_wise_Dec2025 (Rajya Sabha annexure) ¦ State_wise_Jan2026 (PRS from portal) ¦ Pre_Scheme_Baseline ¦ Sources
Caveat on sourcing: pmsuryaghar.gov.in blocks automated access, so portal-dashboard figures (Aug 2026 rows) are taken as reported second-hand by JMK Research / Urban Acres and are marked 'portal via secondary'. Everything else is from a primary government document.
PART 2: SOLAR PUMPS - PM-KUSUM (Pradhan Mantri Kisan Urja Suraksha evam Utthaan Mahabhiyaan), MNRE. Launched 8 Mar 2019, outlay Rs 34,422 crore.
CURRENT TARGET: 14 lakh standalone solar pumps (Component B) + 35 lakh grid-connected pumps solarised (Component C: 1.5 lakh individual + 33.5 lakh feeder-level) = 49 lakh pumps, plus 10,000 MW of small farmer-owned plants (Component A); 34.8 GW in all. Scheme period ended 31 Mar 2026; MNRE OM of 28 Mar 2026 lets projects sanctioned by 31 Dec 2025 complete by 31 Mar 2027. PM-KUSUM 2.0 (~Rs 50,000 cr) is cleared by EFC but not yet approved by Cabinet (Sep 2026).
LATEST OFFICIAL: 28,38,970 pumps solarised as on 31 Jul 2026 (Lok Sabha, 12 Aug 2026). Component B ~11.8 lakh standalone pumps (Aug 2026, portal); Component C ~16.3 lakh (Jun 2026, portal); Component A 1,726.92 MW (Jun 2026).
ANNUAL ADDITIONS: same caveat as rooftop - MNRE reports cumulative 'as on' figures only. KUSUM_Annual_Additions derives yearly numbers; FY24, FY25 and FY26 year-ends are interpolated between official datapoints and shaded yellow. Component B added roughly 0.9 lakh (FY24), 4.3 lakh (FY25), 3.2 lakh (FY26) pumps; Component C went from ~0.1 lakh to ~14 lakh over FY25-FY26 almost entirely via feeder-level solarisation.
Sheets: KUSUM_Annual_Additions ¦ KUSUM_Timeline ¦ KUSUM_Targets ¦ KUSUM_State_wise_Jul2025

## Timeline
As on date | RTS systems installed (nos.) | Households benefitted (nos.) | Applications received (nos.) | Capacity installed (MW) | CFA / subsidy released (Rs crore) | Zero-bill households (nos.) | Source type | Who / document | Source URL | Notes
2024-02-13 | [6 empty] | PIB | Scheme launch by PM; Cabinet approval 29 Feb 2024 (PIB 2010133) | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2010133 | Target: 1 crore households; outlay Rs 75,021 cr; 30 GW residential rooftop
2024-11-30 | 400000 |  |  |  | 3100 |  | PIB | PIB 2080833, 5 Dec 2024 (subsidy disbursed to >4 lakh consumers by Nov 2024) | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2080833 | Column B here = consumers who received subsidy, not installations
2024-12-03 | 630000 |  | 2638000 |  |  |  | PIB | PIB 2080833 / 2081250, 5 Dec 2024: 6.3 lakh installations in 9 months, avg 70,000/month; 1.45 crore registrations | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2081250 | Roadmap stated: 10 lakh by Mar 2025, 20 lakh by Oct 2025, 40 lakh by Mar 2026, 1 crore by Mar 2027
2025-03-10 | 1009000 |  | 4730000 | 3000 | 4770 |  | PIB | PIB 2110283, 13 Mar 2025: 10.09 lakh installations; 6.13 lakh subsidies paid; >3 GW | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2110283 | Closest official datapoint to FY2024-25 year-end
2025-09-23 |  | 2000000 |  |  |  |  | Press (MNRE Secretary) | Tribune, 23 Sep 2025: ~20 lakh households covered; 15-20 lakh to be added in FY26, 30-40 lakh next year | https://www.tribuneindia.com/news/business/mnre-secretary-hopeful-of-achieving-one-crore-rooftop-solar-installations-under-pm-suryaghar-in-quick-time/amp | Rounded figure
2025-12-03 | 1917698 | 2396497 | 5354099 |  |  |  | Rajya Sabha / PIB | PIB 2200441, MoS Shripad Naik, RS written reply 8 Dec 2025; 23.96% of target; FY26 target 35 lakh households | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2200441
2025-12-09 | 1945758 | 2435196 |  | 7075.78 | 13926.25 | 771580 | Rajya Sabha / PIB | PIB 2204466, MoS Naik, RS written reply 16 Dec 2025, state-wise annexure; 7,075.78 MW per AIR 9 Dec 2025 | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2204466 | Full state-wise table in State_wise_Dec2025 sheet
2025-12-31 | 2085514 | 2614446 |  |  | 14771.82 |  | Rajya Sabha | MoS Naik, RS written reply, Feb 2026 (reported SolarQuarter 4 Feb 2026) | https://solarquarter.com/2026/02/04/india-expands-distributed-solar-footprint-under-pm-surya-ghar-with-20-85-lakh-installations-and-26-lakh-beneficiaries/ | Calendar-year 2025 end anchor
2026-01-10 | 2143149 | 2684400 | 5561902 |  |  |  | National Portal via PRS | PRS Demand for Grants 2026-27 analysis, Table 7 (portal data as on 10 Jan 2026) | https://prsindia.org/files/budget/budget_parliament/2026/DfG_Analysis_2026-27-Power.pdf | State-wise in State_wise_Jan2026 sheet
2026-03-05 | 2502217 | [5 empty] | Rajya Sabha | MoS Power, RS reply, Mar 2026 | https://www.socialnews.xyz/2026/03/10/over-25-lakh-rooftop-solar-systems-installed-under-pm-surya-ghar-yojana
2026-03-16 | 2587685 | 3202697 |  |  |  |  | Lok Sabha | Minister Pralhad Joshi, LS reply 18 Mar 2026 (Down To Earth 'As told to Parliament') | https://www.downtoearth.org.in/governance/as-told-to-parliament-march-18-2026-surya-ghar-yojana-benefitting-3202697-households-says-centre
2026-03-19 | 2619879 | 3240000 |  | 9560 | 17967.53 |  | Parliament / PIB | MoS Naik reply 24-25 Mar 2026: 26,19,879 systems, 9.56 GW, 32.4 lakh households, CFA Rs 17,967.53 cr | https://solarquarter.com/2026/03/25/pm-surya-ghar-yojana-updates-2026-26-lakh-rooftop-solar-installations-across-india-with-%E2%82%B917967-crore-central-financial-assistance/ | Closest official datapoint to FY2025-26 year-end
2026-05-31 | 3300000 | 4000000 | 6500000 | 12000 | 22750 | 1700000 | PIB | PIB 2268992, 4 Jun 2026: >33 lakh systems, >40 lakh households, >12 GW, Rs 22,750 cr; May 2026 record 3.16 lakh installations; 75 lakh target by Dec 2026 | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2268992 | Rounded ('more than')
2026-07-20 | 3938805 | 4747341 | 7647000 | 14070 | 27323.55 | 1893000 | Lok Sabha | LS Unstarred Q.580 answered 22 Jul 2026 (MoS Naik) + LS reply reported Energetica 24 Jul 2026 | https://sansad.in/getFile/lsapps/loksabhaquestions/annex/188/AU580_5TGlZa.pdf | LS Starred Q.59 same day reaffirms 1 crore by FY2026-27; Tamil Nadu district-wise annexure
2026-07-22 | 3972447 | 4802717 |  |  |  | 1890000 | Rajya Sabha | MoS Naik, RS written reply 29 Jul 2026 (SolarQuarter) | https://solarquarter.com/2026/07/29/pm-surya-ghar-scheme-nears-4-million-rooftop-solar-installations-over-1-89-million-households-report-zero-power-bills/ | Budget spend: FY25 Rs 7,822.92 cr; FY26 Rs 16,166.23 cr; FY27 BE Rs 22,000 cr (Rs 10,392 cr spent to 22 Jul 2026)
2026-07-31 |  | 5006000 |  | 14800 | 28024 | 1900000 | MNRE / PIB | MNRE release 4 Aug 2026 (DD India / pv magazine): 50.06 lakh households; July 2026 record 5.06 lakh; 14.8 GW; vs 7.94 lakh in prior decade | https://ddindia.co.in/2026/08/pm-surya-ghar-scheme-crosses-50-lakh-rooftop-solar-installations/ | Households, not systems
2026-08-10 | 4190000 | 5040000 | 7770000 | 14894.95 | 28390.5 |  | Rajya Sabha | MoS Naik, RS reply ~11 Aug 2026 (Hans India): 41.9 lakh systems, 50.4 lakh households, 14,894.95 MW, Rs 28,390.50 cr | https://www.thehansindia.com/amp/business/pm-surya-ghar-scheme-receives-777-million-applications-installs-419-million-solar-systems-1108246 | Latest Parliament datapoint; FY2026-27 YTD anchor (official)
2026-08-31 | 4644000 | 5528000 | 8062000 | 16369 | 30885 |  | Portal via secondary | PMSG:MBY portal data compiled by JMK Research, reported Urban Acres 5 Sep 2026: 46.44 lakh installations, 55.28 lakh households, 16,369 MW; alt snapshot 54,65,417 hh / 16,185.48 MW | https://urbanacres.in/pm-surya-ghars-rooftop-solar-push-reveals-a-scale-up-gap/ | NOT a primary government document; portal blocks automated access so could not be verified directly

## Annual_Additions
Period | Anchor date used (end of period) | Cumulative RTS systems at anchor | Cumulative households at anchor | Systems added in period | Households added in period | Official target for the period (households) | Achievement vs target | Basis / caveat
Pre-scheme decade (2014 to Feb 2024) |  | 794000 |  | 794000 |  |  |  | MNRE, Aug 2026: 7.94 lakh residential rooftop installations in the decade before the scheme (~80,000/yr; ~7,000/month per Minister Joshi, Jun 2026)
FY 2023-24 (13 Feb - 31 Mar 2024) | 2024-03-31 | [6 empty] | Negligible; scheme launched 13 Feb 2024, subsidy disbursal only began Jun 2024 after elections. No official figure published.
FY 2024-25 | [7 empty] | Anchor = 10 Mar 2025 (10.09 lakh systems). True 31 Mar 2025 figure not published; at the then run-rate (~1 lakh/month) FY25 close is ~10.7-11 lakh systems.
FY 2025-26 | [5 empty] | 3500000 |  | Achievement = systems added / household target (slightly understates, since households > systems). Anchor = 19 Mar 2026 (26,19,879 systems / 32.4 lakh households). Target 35 lakh households for FY26 (RS, 8 Dec 2025). Households added in FY26 ~ 19-20 lakh if FY25-end households were ~13 lakh (not published).
FY 2026-27 YTD (Apr - ~10 Aug 2026), official | [7 empty] | Anchor = Rajya Sabha reply ~10 Aug 2026 (41.9 lakh systems / 50.4 lakh households). About 4.5 months of FY27.
FY 2026-27 YTD (Apr - Aug 2026), portal | [7 empty] | Anchor = portal snapshot end-Aug 2026 via JMK/Urban Acres (46.44 lakh systems / 55.28 lakh households). Secondary source.
Calendar 2024 (13 Feb - 3 Dec 2024) | [7 empty] | PIB 5 Dec 2024: 6.3 lakh installations in first 9 months. CY2024 close likely ~7 lakh.
Calendar 2025 | [7 empty] | 31 Dec 2025 official: 20,85,514 systems / 26,14,446 households (RS reply). Households added in CY2025 ~ 18-19 lakh (CY2024-end households not published).
Calendar 2026 YTD (Jan - ~10 Aug 2026), official | [5 empty] | 7500000 |  | Target column = Minister's stated 75 lakh households by Dec 2026 (PIB 4 Jun 2026); achievement = cumulative households at anchor / 75 lakh. Households added Jan-Aug 2026 ~ 24 lakh.
Cumulative since launch to ~10 Aug 2026 | [5 empty] | 10000000 |  | Scheme target: 1 crore households by FY 2026-27 (31 Mar 2027). ~50% reached with ~7.5 months left; MNRE Secretary (15 Sep 2026) expects 85-90 lakh by Mar 2027.
Yellow = derived by subtraction between nearest official cumulative datapoints; anchors are not exact year-ends. Formulas link to the Timeline sheet.

## Targets
Target / milestone | Value | Deadline | Set by / stated in | Date stated | Status as of Sep 2026 | Source URL
Scheme target (households) | 1 crore (10,000,000) households | FY 2026-27 (31 Mar 2027) | Union Cabinet approval; reaffirmed LS Starred Q.59, 22 Jul 2026 | 2024-02-29 | ~50.4 lakh households by ~10 Aug 2026 (official); 55.28 lakh end-Aug (portal). MNRE Secretary (15 Sep 2026): 85-90 lakh likely by Mar 2027. | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2010133
Scheme target (capacity) | 30 GW residential rooftop | Mar 2027 | Cabinet approval; PIB 10-lakh release said '27 GW more by Mar 2027' | 2024-02-29 | 14,894.95 MW by Aug 2026 (RS); ~16.4 GW end-Aug (portal). Roughly half. | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2110283
Financial outlay | Rs 75,021 crore | FY 2026-27 | Cabinet | 2024-02-29 | Rs 28,390.50 cr CFA released to Aug 2026 (RS). Budget: FY25 actual 7,822.92 cr; FY26 actual 16,166.23 cr (BE 20,000); FY27 BE 22,000 cr. | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2010133
Interim roadmap (PIB, Dec 2024) | 10 lakh by Mar 2025; 20 lakh by Oct 2025; 40 lakh by Mar 2026; 1 crore by Mar 2027 | see value | PIB 2080833 / 2081250 | 2024-12-05 | 10 lakh: met (10 Mar 2025). 20 lakh by Oct 2025: ~20 lakh households by Sep 2025 (met on households, not systems). 40 lakh by Mar 2026: MISSED (26.2 lakh systems / 32.4 lakh households). | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2081250
Annual target FY 2025-26 | 35 lakh households | 31 Mar 2026 | MoS Shripad Naik, Rajya Sabha written reply | 2025-12-08 | MISSED: ~16 lakh systems / ~19-20 lakh households added in FY26 (derived). | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2200441
MNRE Secretary projection FY26 / FY27 | 15-20 lakh added in FY 2025-26; 30-40 lakh in FY 2026-27 | Mar 2027 | Secretary Santosh Kumar Sarangi (press) | 2025-09-23 | FY26 landed inside the 15-20 lakh range. FY27 pace (Apr-Aug ~18-21 lakh households in 5 months) is ahead of the 30-40 lakh projection. | https://www.tribuneindia.com/news/business/mnre-secretary-hopeful-of-achieving-one-crore-rooftop-solar-installations-under-pm-suryaghar-in-quick-time/amp
Interim target (Minister) | 75 lakh households | Dec 2026 | Minister Pralhad Joshi, 'Two years of PM Surya Ghar' event, PIB 2268992 | 2026-06-04 | Needs ~20-25 lakh more households in Sep-Dec 2026, i.e. ~5-6 lakh/month vs July 2026 record 5.06 lakh. Achievable only if the July pace holds. | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2268992
Secretary's revised expectation | 85-90 lakh households | Mar 2027 | MNRE Secretary Sarangi (press) | 2026-09-15 | Implicit admission that 1 crore by Mar 2027 is unlikely. No official revision of the 1 crore target or of the 31 Mar 2027 scheme end has been notified. | https://www.energetica-india.net/news/pm-surya-ghar-scheme-crosses-50-lakh-rooftop-solar-installations-14-8-gw-capacity-commissioned
Utility-Led Aggregation (ULA) pipeline | ~30 lakh installations planned via DISCOMs | n/a | Minister Joshi, PIB 2268992 | 2026-06-04 | Pipeline, not achievement. | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2268992

## Monthly_RunRate
Period | Installations / households per month | Per day | Capacity added in month (MW) | Source
Pre-scheme (before Feb 2024) | 7000 |  |  | Minister Joshi, PIB 2268992 (4 Jun 2026): 'about 7,000 per month before the scheme'
Feb-Nov 2024 average | 70000 |  |  | PIB 2080833 (5 Dec 2024): 6.3 lakh in 9 months, ~70,000/month
Oct 2025 |  | 5038 |  | MNRE release 4 Aug 2026: 5,038 installations per day
Mar 2026 (5-19 Mar) | 252000 |  |  | Derived: 25,02,217 (5 Mar) to 26,19,879 (19 Mar) = 1.18 lakh in 14 days
May 2026 | 316000 | 15000 |  | PIB 2268992: record 3.16 lakh installations; 15,000 in one day
Jul 2026 | 506000 | 16328 | 1592 | MNRE release 4 Aug 2026 (households); JMK/Urban Acres for MW
Aug 2026 |  |  | 1407 | JMK/Urban Acres (portal): ~1,407 MW, 11.6% below July

## State_wise_Dec2025
S No. | State/UT | RTS installations (nos.) | Households benefitted (nos.) | Consumers with zero energy charges (nos.) | CFA disbursed (nos.) | CFA amount (Rs crore) | Loan applications sanctioned (nos.)
1 | Andhra Pradesh | 76617 | 79210 | 36381 | 66070 | 511.11 | 61607
2 | Arunachal Pradesh | 1 | 1 | 0 | 1 | 0.01 | 74
3 | Assam | 63887 | 64525 | 4973 | 51894 | 442.26 | 69883
4 | Bihar | 13649 | 14096 | 0 | 12640 | 97.5 | 9204
5 | Chhattisgarh | 16498 | 17847 | 987 | 10900 | 84.42 | 16121
6 | Goa | 1304 | 1596 | 798 | 1110 | 8.78 | 264
7 | Gujarat | 493161 | 710102 | 362675 | 474051 | 3714.47 | 42408
8 | Haryana | 44937 | 50434 | 1575 | 41921 | 310.16 | 18717
9 | Himachal Pradesh | 5556 | 5679 | 502 | 5018 | 42.94 | 2994
10 | Jharkhand | 1308 | 1310 | 357 | 1146 | 8.89 | 997
11 | Karnataka | 14471 | 22833 | 245 | 13456 | 108.68 | 4426
12 | Kerala | 169227 | 174097 | 117697 | 155907 | 1216.82 | 76421
13 | Madhya Pradesh | 78062 | 81361 | 40594 | 73299 | 570.24 | 37602
14 | Maharashtra | 363811 | 580271 | 105003 | 328640 | 2613.21 | 138592
15 | Manipur | 680 | 680 | 139 | 629 | 5.37 | 296
16 | Meghalaya | 32 | 32 | 2 | 26 | 0.15 | 692
17 | Mizoram | 727 | 729 | 156 | 649 | 5.49 | 4
18 | Nagaland | 129 | 129 | 0 | 121 | 1.01 | 28
19 | Odisha | 23774 | 24125 | 3949 | 19763 | 151.2 | 22324
20 | Punjab | 10456 | 10566 | 0 | 9488 | 73.85 | 4140
21 | Rajasthan | 108584 | 111521 | 8472 | 98064 | 763.8 | 65455
22 | Sikkim | 23 | 23 | 0 | 14 | 0.12 | 12
23 | Tamil Nadu | 48652 | 56258 | 0 | 44355 | 334.85 | 11801
24 | Telangana | 23675 | 34110 | 10234 | 21215 | 168.51 | 12060
25 | Tripura | 1603 | 1614 | 178 | 1344 | 11.28 | 1366
26 | Uttarakhand | 55229 | 55391 | 23367 | 48214 | 413.5 | 32016
27 | Uttar Pradesh | 302140 | 305397 | 42707 | 271181 | 2074.53 | 186297
28 | West Bengal | 1107 | 1170 | 20 | 330 | 2.46 | 1006
29 | Andaman and Nicobar Islands | 147 | 166 | 24 | 128 | 1.08 | 93
30 | Chandigarh | 957 | 957 | 148 | 695 | 5.31 | 121
31 | Jammu and Kashmir | 15985 | 15985 | 3958 | 13616 | 116.55 | 10993
32 | Ladakh | 1077 | 1077 | 2744 | 944 | 8.1 | 26
33 | Lakshadweep | 685 | 685 | 1126 | 651 | 5.59 | 260
34 | NCT of Delhi | 5059 | 8671 | 1733 | 4349 | 36.27 | 1228
35 | Puducherry | 2066 | 2066 | 785 | 1849 | 14.22 | 961
36 | DNH&DD | 482 | 482 | 51 | 453 | 3.52 | 128
Total
Source: Annexure to Rajya Sabha written reply by MoS Shripad Yesso Naik, 16 Dec 2025, as on 09.12.2025 (PIB Release ID 2204466). Official totals: 19,45,758 systems; 24,35,196 households; 7,71,580 zero-bill; Rs 13,926.25 cr CFA. https://www.pib.gov.in/PressReleasePage.aspx?PRID=2204466

## State_wise_Jan2026
State/UT | Applications | Installations (nos.) | Installations as % of applications | Households covered
Andaman and Nicobar | 654 | 183 |  | 202
Andhra Pradesh | 1175634 | 87984 |  | 90864
Arunachal Pradesh | 88 | 1 |  | 1
Assam | 484444 | 75177 |  | 75883
Bihar | 55543 | 14500 |  | 15148
Chandigarh | 1510 | 1001 |  | 1001
Chhattisgarh | 121687 | 23404 |  | 24825
Dadra & Nagar Haveli and Daman & Diu | 1949 | 496 |  | 496
Delhi | 17149 | 5589 |  | 9471
Goa | 2687 | 1461 |  | 1814
Gujarat | 617917 | 524808 |  | 757016
Haryana | 104038 | 49473 |  | 56562
Himachal Pradesh | 10719 | 6234 |  | 6235
Jammu and Kashmir | 90917 | 19459 |  | 19467
Jharkhand | 7886 | 1512 |  | 1514
Karnataka | 155643 | 15292 |  | 24168
Kerala | 243706 | 180783 |  | 185462
Ladakh | 1725 | 1278 |  | 1278
Lakshadweep | 1144 | 752 |  | 752
Madhya Pradesh | 139368 | 85955 |  | 89367
Maharashtra | 589328 | 403698 |  | 650742
Manipur | 1478 | 729 |  | 729
Meghalaya | 1933 | 35 |  | 35
Mizoram | 954 | 787 |  | 789
Nagaland | 548 | 132 |  | 132
Odisha | 161517 | 29396 |  | 29744
Puducherry | 3209 | 2286 |  | 2286
Punjab | 18866 | 10906 |  | 11016
Rajasthan | 249987 | 123248 |  | 127175
Sikkim | 261 | 26 |  | 26
Tamil Nadu | 65809 | 52224 |  | 60831
Telangana | 72956 | 26041 |  | 37155
Tripura | 7871 | 1945 |  | 1956
Uttar Pradesh | 1045349 | 335182 |  | 338861
Uttarakhand | 95316 | 60027 |  | 60189
West Bengal | 12112 | 1145 |  | 1208
All-India
Source: PRS Legislative Research, Demand for Grants 2026-27 Analysis: Power and New & Renewable Energy, Table 7 (PMSG:MBY National Portal, as on 10 Jan 2026). PRS totals: 55,61,902 applications; 21,43,149 installations; 26,84,400 households. https://prsindia.org/files/budget/budget_parliament/2026/DfG_Analysis_2026-27-Power.pdf

## Pre_Scheme_Baseline
Metric | Value | As on | Source
Residential rooftop installations in the decade before PM Surya Ghar | 7.94 lakh (794,000) | Feb 2024 | MNRE release 4 Aug 2026 (DD India / pv magazine): '7.94 lakh in the preceding decade'
Pre-scheme monthly installation rate | ~7,000 per month | 2023 | Minister Pralhad Joshi, PIB 2268992, 4 Jun 2026
Rooftop Solar Programme Phase-II residential target | 4,000 MW residential capacity under CFA | Launched 8 Mar 2019 | PIB 1989806, 23 Dec 2023 (LS reply 21 Dec 2023)
Phase-II residential capacity installed under subsidy | 2,651.10 MW | 30 Nov 2023 | PIB 1989806 (state-wise table; Gujarat 1,956.85 MW of it)
All-sector grid-connected rooftop capacity | 1.8 GW (31 Mar 2019) -> 10.4 GW (30 Nov 2023), CAGR ~46% | 30 Nov 2023 | PIB 1989806
All-sector grid-connected rooftop capacity | 22.42 GW | Oct 2025 | PIB 2199729 (India's Solar Momentum)
All-sector grid-connected rooftop capacity | 32.59 GW | 31 Aug 2026 | MNRE Physical Progress page, https://mnre.gov.in/en/physical-progress/

## Sources
# | Document | Date | Type | URL
1 | Cabinet approves PM-Surya Ghar for 1 crore households (PIB 2010133) | 2024-02-29 | PIB press release | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2010133
2 | PMSGMBY set to surpass 10 lakh by Mar 2025 (PIB 2080833) | 2024-12-05 | PIB press release | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2080833
3 | PM Surya Ghar backgrounder, roadmap to 1 crore (PIB 2081250) | 2024-12-05 | PIB backgrounder | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2081250
4 | Crosses 10 lakh installations (PIB 2110283) | 2025-03-13 | PIB press release | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2110283
5 | MNRE Secretary: 15-20 lakh in FY26, 30-40 lakh next year (Tribune) | 2025-09-23 | Press | https://www.tribuneindia.com/news/business/mnre-secretary-hopeful-of-achieving-one-crore-rooftop-solar-installations-under-pm-suryaghar-in-quick-time/amp
6 | 23.96 lakh households, 35 lakh FY26 target, RS reply (PIB 2200441) | 2025-12-08 | Rajya Sabha / PIB | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2200441
7 | 7,075.78 MW installed under PMSG:MBY (AIR) | 2025-12-09 | Rajya Sabha / AIR | https://www.newsonair.gov.in/7075-78-mw-rooftop-solar-installed-under-pm-surya-ghar-muft-bijli-yojana
8 | Zero bills to 7.7 lakh households, state-wise annexure as on 9 Dec 2025 (PIB 2204466) | 2025-12-16 | Rajya Sabha / PIB | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2204466
9 | India's Solar Momentum: 23.9 lakh households, 7 GW (PIB 2199729) | 2025-12-20 | PIB backgrounder | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2199729
10 | RS reply: 20,85,514 systems / 26,14,446 households as on 31 Dec 2025 (SolarQuarter) | 2026-02-04 | Rajya Sabha via press | https://solarquarter.com/2026/02/04/india-expands-distributed-solar-footprint-under-pm-surya-ghar-with-20-85-lakh-installations-and-26-lakh-beneficiaries/
11 | PRS Demand for Grants 2026-27 analysis, Power & MNRE (Table 7 state-wise, 10 Jan 2026) | 2026-02-10 | PRS | https://prsindia.org/files/budget/budget_parliament/2026/DfG_Analysis_2026-27-Power.pdf
12 | LS reply: 25,87,685 systems / 32,02,697 households as on 16 Mar 2026 (Down To Earth) | 2026-03-18 | Lok Sabha via press | https://www.downtoearth.org.in/governance/as-told-to-parliament-march-18-2026-surya-ghar-yojana-benefitting-3202697-households-says-centre
13 | 26,19,879 systems, Rs 17,967.53 cr CFA as on 19 Mar 2026 (SolarQuarter) | 2026-03-25 | Parliament via press | https://solarquarter.com/2026/03/25/pm-surya-ghar-yojana-updates-2026-26-lakh-rooftop-solar-installations-across-india-with-%E2%82%B917967-crore-central-financial-assistance/
14 | 75 lakh households by Dec 2026, two-year event (PIB 2268992) | 2026-06-04 | PIB press release | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2268992
15 | LS Starred Q.59, 22 Jul 2026: target 1 crore by FY2026-27; TN district-wise | 2026-07-22 | Lok Sabha (sansad.in PDF) | https://sansad.in/getFile/lsapps/loksabhaquestions/annex/188/AS59_dKLc7G.pdf
16 | LS Unstarred Q.580, 22 Jul 2026: 39,38,805 systems / 47,47,341 households / Rs 27,323.55 cr | 2026-07-22 | Lok Sabha (sansad.in PDF) | https://sansad.in/getFile/lsapps/loksabhaquestions/annex/188/AU580_5TGlZa.pdf
17 | LS reply as on 20 Jul 2026: 14.07 GW, 76.47 lakh applications, state leaders (Energetica) | 2026-07-24 | Lok Sabha via press | https://www.energetica-india.net/news/pm-surya-ghar-crosses-39-38-lakh-rooftop-solar-installations-capacity-reaches-14-07-gw
18 | RS reply as on 22 Jul 2026: 39,72,447 systems / 48,02,717 households; budget spend by FY (SolarQuarter) | 2026-07-29 | Rajya Sabha via press | https://solarquarter.com/2026/07/29/pm-surya-ghar-scheme-nears-4-million-rooftop-solar-installations-over-1-89-million-households-report-zero-power-bills/
19 | MNRE: crosses 50 lakh households, July record 5.06 lakh, 7.94 lakh in prior decade (DD India) | 2026-08-04 | MNRE via DD India | https://ddindia.co.in/2026/08/pm-surya-ghar-scheme-crosses-50-lakh-rooftop-solar-installations/
20 | Same MNRE release (pv magazine) | 2026-08-05 | MNRE via press | https://www.pv-magazine.com/2026/08/05/pm-surya-ghar-rooftop-solar-scheme-surpasses-5-million-households/
21 | RS reply Aug 2026: 7.77 mn applications, 4.19 mn systems, 5.04 mn households, 14,894.95 MW, Rs 28,390.50 cr (Hans India) | 2026-08-11 | Rajya Sabha via press | https://www.thehansindia.com/amp/business/pm-surya-ghar-scheme-receives-777-million-applications-installs-419-million-solar-systems-1108246
22 | Portal data via JMK Research: 46.44 lakh systems / 55.28 lakh households / 16,369 MW end-Aug 2026 (Urban Acres) | 2026-09-05 | Portal via secondary | https://urbanacres.in/pm-surya-ghars-rooftop-solar-push-reveals-a-scale-up-gap/
23 | MNRE Secretary: 85-90 lakh by Mar 2027 (Energetica, 50-lakh milestone piece) | 2026-09-15 | Press | https://www.energetica-india.net/news/pm-surya-ghar-scheme-crosses-50-lakh-rooftop-solar-installations-14-8-gw-capacity-commissioned
24 | MNRE Physical Progress: rooftop 32.59 GW all sectors as on 31 Aug 2026 | 2026-08-31 | MNRE | https://mnre.gov.in/en/physical-progress/
25 | Rooftop Solar Programme Phase-II, pre-scheme state-wise capacity (PIB 1989806) | 2023-12-23 | PIB press release | https://www.pib.gov.in/PressReleasePage.aspx?PRID=1989806
26 | PM-KUSUM scheme page (targets, period till 31.03.2026) | 2026-09-01 | MNRE | https://mnre.gov.in/en/pradhan-mantri-kisan-urja-suraksha-evam-utthaan-mahabhiyaan-pm-kusum/
27 | PM-KUSUM factsheet (original 2019 targets) | 2019-02-19 | PIB factsheet | https://www.pib.gov.in/FactsheetDetails.aspx?Id=148576&reg=48&lang=2
28 | PM-KUSUM: 89.45 MW, 2.09 lakh pumps as on 28.02.2023 (PIB 1907703) | 2023-03-16 | Lok Sabha / PIB | https://www.pib.gov.in/PressReleasePage.aspx?PRID=1907703
29 | Progress of PM-KUSUM, RS reply: 2,44,373 pumps as on 30.06.2023 (PIB 1947138) | 2023-08-08 | Rajya Sabha / PIB | https://www.pib.gov.in/PressReleasePage.aspx?PRID=1947138
30 | Mongabay: 2,18,539 pumps to 31.03.2023 (citing MNRE report May 2023) | 2023-09-20 | Press citing MNRE | https://india.mongabay.com/2023/09/under-utilisation-of-off-grid-standalone-solar-pumps-remains-a-challenge/
31 | Progress and implementation of PM-KUSUM, state-wise as on 30.11.2023 (PIB 1989815) | 2023-12-23 | Lok Sabha / PIB | https://www.pib.gov.in/PressReleasePage.aspx?PRID=1989815
32 | 2.95 lakh standalone pumps, state-wise as on 31.01.2024 (PIB 2004183) | 2024-02-08 | Lok Sabha / PIB | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2004183
33 | 4,11,222 farmers benefited as on 30.06.2024 (PIB 2042069) | 2024-08-06 | PIB | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2042069
34 | PM-KUSUM 42% of pump target, 5,40,499 as on 31.10.2024 (Energetica, LS reply) | 2024-11-29 | Lok Sabha via press | https://www.energetica-india.net/news/-pm-kusum-achieves-42-percent-solar-pump-installation-target
35 | 319.23 MW / 5.4 lakh / 80,845 as on 31.10.2024 (Energetica, RS reply) | 2024-12-04 | Rajya Sabha via press | https://energetica-india.net/news/pm-kusum-scheme-31923-mw-installed-54-lakh-pumps-deployed-80845-pumps-solarised
36 | Standing Committee on Energy, 5th Report, DfG 2025-26 MNRE (achievements 31.01.2025; FY26 targets) | 2025-03-10 | Lok Sabha committee | https://sansad.in/getFile/lsscommittee/Energy/18_Energy_5.pdf?source=loksabhadocs
37 | Standing Committee on Energy, 10th Report, Performance of Solar Projects (progress 30.06.2025; Annexure IV 31.07.2025) | 2025-09-01 | Lok Sabha committee | https://sansad.in/getFile/lsscommittee/Energy/18_Energy_10.pdf?source=loksabhadocs
38 | Committee on Estimates, 7th Report, PM-KUSUM & PM Surya Ghar (table 31.07.2025; targets 49 lakh; year-wise funds) | 2025-12-04 | Lok Sabha committee | https://sansad.in/getFile/lsscommittee/Estimates/18_Estimates_7.pdf?source=loksabhadocs
39 | LS reply 10 Dec 2025: 10.9 lakh pumps solarised, Rs 7,106 cr (SolarQuarter) | 2025-12-11 | Lok Sabha via press | https://solarquarter.com/2025/12/11/indias-pm-kusum-progress-over-10-9-lakh-pumps-solarized-and-%E2%82%B97106-crore-support-released/
40 | Down To Earth: Centre readies PM-KUSUM 2.0 (component split Nov 2025; EFC approval) | 2025-12-30 | Press | https://www.downtoearth.org.in/energy/centre-readies-pm-kusum-20-as-focus-shifts-to-feeder-level-solarisation
41 | PRS DfG 2026-27 analysis Table 3 (PM-KUSUM portal, 9 Feb 2026) | 2026-02-10 | PRS | https://prsindia.org/files/budget/budget_parliament/2026/DfG_Analysis_2026-27-Power.pdf
42 | Minister Joshi 11 Mar 2026: >10 lakh standalone, >13 lakh grid pumps | 2026-03-11 | Press | https://www.thehawk.in/news/science/over-10-lakh-standalone-solar-pumps-installed-13-lakh-grid-connected-pumps-solarised
43 | MNRE extends PM-KUSUM completion deadline to 31 Mar 2027 (OM 28 Mar 2026) | 2026-03-30 | MNRE via press | https://www.energetica-india.net/news/mnre-extends-pm-kusum-project-completion-deadline-to-march-31-2027
44 | UnderstandUPSC: 31.12.2025 component figures placed in Parliament Mar 2026 | 2026-04-01 | Secondary | https://www.understandupsc.com/pm-kusum/
45 | Franchise India: dashboard figures 30.04.2026 and Aug 2026 | 2026-08-20 | Secondary (portal) | https://www.franchiseindia.com/insights/en/article/pm-kusum-component-b-guide-2026-subsidy-tender-vendor-selection-and-allocation-process.59738
46 | Saur Energy: dashboard figures 30.06.2026 | 2026-07-21 | Secondary (portal) | https://www.saurenergy.com/solar-energy-news/pm-kusums-missing-link-why-indias-solar-pump-success-isnt-yet-an-agricultural-energy-revolution-12183450
47 | LS reply Jul 2026: 13.11 GW by 31.03.2026, Comp-A 1,726.92 MW (Energetica) | 2026-07-26 | Lok Sabha via press | https://www.energetica-india.net/news/pm-kusum-scheme-installs-1311-gw-by-march-2026-ppa-projects-extended-until-march-2027
48 | LS reply 12 Aug 2026: 28,38,970 pumps solarised as on 31.07.2026; Rs 10,850.8 cr (ANI) | 2026-08-12 | Lok Sabha via press | https://aninews.in/news/business/over-51-lakh-households-benefit-under-pm-surya-ghar-284-lakh-farm-pumps-solarised-govt20260812131651/
49 | Minister Joshi 9 Sep 2026: PM-KUSUM 2.0 'set to be announced anytime' (Reslink) | 2026-09-09 | Press | https://www.reslink.org/blogs/pm-kusum-2-0-is-coming-india-s-rs-50-000-crore-agricultural-solar-push/

## KUSUM_Timeline
As on date | Comp-B standalone pumps installed (nos.) | Comp-B sanctioned (nos.) | Comp-C IPS solarised (nos.) | Comp-C FLS pumps solarised (nos.) | Comp-C total solarised (nos.) | All pumps B+C (nos.) | Comp-A installed (MW) | CFA released (Rs crore) | Source type | Who / document | Source URL | Notes
2019-03-08 | [8 empty] | MNRE | Scheme launched 8 Mar 2019 (approved 19 Feb 2019); outlay Rs 34,422 cr | https://mnre.gov.in/en/pradhan-mantri-kisan-urja-suraksha-evam-utthaan-mahabhiyaan-pm-kusum/ | Original: 10,000 MW (A), 20 lakh pumps (B), 15 lakh pumps (C) by 2022
2020-03-31 | 8954 | [6 empty] | 151.26 | MNRE year-end review | MNRE Year End Review 2020: 8,954 standalone pumps installed in 2019-20 | https://www.manoramayearbook.in/current-affairs/india/2021/01/05/ministry-of-new-and-renewable-energy-mnre-year-end-review.html | CFA = funds utilised FY20 (Standing Committee DfG 2025-26)
2021-03-31 | 40000 | [6 empty] | 156.43 | MNRE | MNRE: over 40,000 pumps reported installed up to 31.03.2021 | https://mnre.gov.in/en/pradhan-mantri-kisan-urja-suraksha-evam-utthaan-mahabhiyaan-pm-kusum/ | Rounded ('over 40,000'); CFA = FY21 funds utilised
2023-02-28 | [5 empty] | 208648 | 89.45 |  | Lok Sabha / PIB | PIB 1907703, LS reply Mar 2023: 2.09 lakh pumps solarised; 89.45 MW | https://www.pib.gov.in/PressReleasePage.aspx?PRID=1907703 | Total pumps (B + small C); state-wise annexure
2023-03-31 | 218539 | [6 empty] | 801.36 | MNRE report (via Mongabay) | MNRE report May 2023 cited by Mongabay Sep 2023: ~2,18,539 standalone pumps to 31.03.2023 | https://india.mongabay.com/2023/09/under-utilisation-of-off-grid-standalone-solar-pumps-remains-a-challenge/ | Secondary citation of an MNRE report; CFA = FY23 funds utilised
2023-06-30 | 244373 | 947991 | 1519 |  | 1519 | 245892 |  |  | Rajya Sabha / PIB | PIB 1947138, RS reply 8 Aug 2023 (R.K. Singh): 2,44,373 B installed vs 9,47,991 allocated; 1,519 C solarised | https://www.pib.gov.in/PressReleasePage.aspx?PRID=1947138
2023-11-30 | 278114 | 971471 |  |  | 4594 | 282708 | 141.33 |  | Lok Sabha / PIB | PIB 1989815, LS reply 21 Dec 2023: state-wise table | https://www.pib.gov.in/PressReleasePage.aspx?PRID=1989815 | C sanctioned: IPS 1,34,286; FLS 29,12,466
2024-01-31 | 295823 | 1294787 |  |  | 7384 | 303207 | 165.28 |  | Lok Sabha / PIB | PIB 2004183, LS reply 8 Feb 2024: state-wise table | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2004183 | C sanctioned: IPS 1,61,204; FLS 33,76,466. Closest official datapoint to FY2023-24 year-end
2024-06-30 | [5 empty] | 411222 |  |  | PIB | PIB 2042069, 6 Aug 2024: 4,11,222 farmers benefited (B+C) | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2042069 | Farmers, not pumps
2024-10-31 | 540499 | 1302327 |  |  | 80845 | 621344 | 319.23 | 3748.61 | Lok Sabha & Rajya Sabha | MoS Naik, LS reply 28 Nov 2024 / RS reply Dec 2024 (Energetica): B 42% of sanctioned; CFA utilised Rs 3,748.61 cr of Rs 11,438 cr | https://www.energetica-india.net/news/-pm-kusum-achieves-42-percent-solar-pump-installation-target | C sanctioned 34.65 lakh
2025-01-31 | 669484 |  | 5272 | 187633 | 192905 | 862389 | 417.98 |  | Standing Committee on Energy | 5th Report, Demands for Grants 2025-26 (MNRE), para 4.18: achievements as on 31.01.2025 | https://sansad.in/getFile/lsscommittee/Energy/18_Energy_5.pdf?source=loksabhadocs | FLS 653.80 MW = 1,87,633 pumps. Closest official datapoint to FY2024-25 year-end
2025-06-30 | 840000 | 1330000 |  |  | 590000 | 1430000 | 639 |  | Standing Committee on Energy | 10th Report (Sep 2025), para 3.11 graphs: B 8.4 lakh installed / 13.3 lakh sanctioned; C 5.9 lakh / 35.6 lakh; A 639 MW | https://sansad.in/getFile/lsscommittee/Energy/18_Energy_10.pdf?source=loksabhadocs | Read off bar-chart labels (lakh, one decimal)
2025-07-31 | 853349 | 1272758 | 8966 | 645975 | 654941 | 1508290 | 640.99 |  | Committee on Estimates | 7th Report (4 Dec 2025), table as on 31.07.2025: A 640.99/10,000 MW; B 8,53,349/12,72,758; IPS 8,966/60,828; FLS 6,45,975/35,61,855 | https://sansad.in/getFile/lsscommittee/Estimates/18_Estimates_7.pdf?source=loksabhadocs | Also state-wise B table (Energy 10th Report Annexure IV, total 8,53,330)
2025-10-31 | 920000 | [7 empty] | PIB | PIB 2199729 'India's Solar Momentum' (Dec 2025): close to 9.2 lakh standalone pumps | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2199729 | Rounded; as-on date approximate (Oct/Nov 2025)
2025-11-30 | 942189 | 1308644 |  |  | 1099699 | 2041888 | 667.3 | 7106 | Lok Sabha | LS reply 10 Dec 2025 (SolarQuarter / Down To Earth): 'over 10.9 lakh pumps solarised' (= Component C); CFA Rs 7,106 cr; 10,203 MW total | https://www.downtoearth.org.in/energy/centre-readies-pm-kusum-20-as-focus-shifts-to-feeder-level-solarisation | Component split per Down To Earth: A 667.3/9,964 MW; B 9,42,189/13,08,644; C 10,99,699/35,83,320. 'Over 10.9 lakh pumps solarised' headline = Component C only
2025-12-31 | 975227 | 1315190 |  |  | 1201552 | 2176779 |  |  | Parliament (via secondary) | Data placed in Parliament Mar 2026, cited by UnderstandUPSC: B 9,75,227 (4,398.57 MW); C 12,01,552 (5,829.98 MW) | https://www.understandupsc.com/pm-kusum/ | Secondary citation; calendar-2025 year-end anchor
2026-02-09 | 1000000 | 1300000 | 12311 |  |  |  | 765 |  | National Portal via PRS | PRS DfG 2026-27 analysis Table 3 (PM-KUSUM portal, 9 Feb 2026): B 10 lakh / 13 lakh (76%); IPS 12,311 / 55,392 (22%); A 765 / 10,000 MW (8%) | https://prsindia.org/files/budget/budget_parliament/2026/DfG_Analysis_2026-27-Power.pdf | Rounded to lakh
2026-03-11 | 1000000 |  |  |  | 1300000 | 2300000 |  |  | Minister statement | Minister Joshi, 11 Mar 2026: 'more than 10 lakh standalone pumps installed, over 13 lakh grid-connected pumps solarised' | https://www.thehawk.in/news/science/over-10-lakh-standalone-solar-pumps-installed-13-lakh-grid-connected-pumps-solarised | Rounded
2026-03-31 | [6 empty] | 13110 |  | Lok Sabha | LS reply Jul 2026 (Energetica 26 Jul 2026): 13.11 GW total installed under PM-KUSUM as on 31.03.2026; extension to Mar 2027 for PPA/NTP by 31.12.2025 | https://www.energetica-india.net/news/pm-kusum-scheme-installs-1311-gw-by-march-2026-ppa-projects-extended-until-march-2027 | Column H here = ALL components (GW x1000), not Comp-A
2026-04-30 | 1090815 | 1307190 | 15183 | 1571826 | 1587009 | 2677824 |  |  | Portal via secondary | MNRE PM-KUSUM dashboard as on 30.04.2026, cited by Franchise India / SurgePV | https://www.franchiseindia.com/insights/en/article/pm-kusum-component-b-guide-2026-subsidy-tender-vendor-selection-and-allocation-process.59738 | Sanctioned: IPS 55,392; FLS 35,36,602. Not verified against a primary document
2026-06-30 | 1149988 | 1307190 | 15822 | 1617058 | 1632880 | 2782868 | 1726.92 |  | Portal via secondary + Lok Sabha | MNRE dashboard 30.06.2026 (Saur Energy 21 Jul 2026); Comp-A 1,726.92 MW also in LS reply Jul 2026 | https://www.saurenergy.com/solar-energy-news/pm-kusums-missing-link-why-indias-solar-pump-success-isnt-yet-an-agricultural-energy-revolution-12183450 | B = 88% of sanctioned; FLS 45.7%; IPS 28.6%
2026-07-31 | [5 empty] | 2838970 | 4116.89 | 10850.8 | Lok Sabha | LS reply 12 Aug 2026 (ANI / Asianet): 28,38,970 pumps solarised under PM-KUSUM as on 31.07.2026; Rs 10,850.8 cr CFA released 2023-24 to Jul 2026; 4,116.89 MW | https://aninews.in/news/business/over-51-lakh-households-benefit-under-pm-surya-ghar-284-lakh-farm-pumps-solarised-govt20260812131651/ | Latest Parliament datapoint. 4,116.89 MW as reported ('off-grid solar / PM-KUSUM'); treat with caution. CFA figure covers 2023-24 onward only
2026-08-31 | 1180474 | 1307190 | [6 empty] | Portal via secondary | MNRE dashboard Aug 2026 (cited by Franchise India): 11,80,474 standalone pumps | https://www.franchiseindia.com/insights/en/article/pm-kusum-component-b-guide-2026-subsidy-tender-vendor-selection-and-allocation-process.59738 | Not verified against a primary document

## KUSUM_Annual_Additions
Financial year | Anchor date for year-end | Comp-B cumulative standalone pumps at year-end | Comp-B pumps added in year | Comp-C cumulative solarised pumps at year-end | Comp-C pumps added in year | All pumps (B+C) cumulative | Annual target set by MNRE | Basis / caveat
FY 2019-20 | 2020-03-31 |  |  | 0 | 0 |  |  | MNRE Year End Review 2020: 8,954 pumps installed in 2019-20. Scheme launched Mar 2019.
FY 2020-21 | 2021-03-31 |  |  | 0 | 0 |  | Comp-B 2020-21 targets exceeded demand (Estimates Cttee para 2.51) | MNRE: 'over 40,000' installed up to 31.03.2021 (rounded). COVID years; Ministry told the Committee 'first two years were lost to COVID-19'.
FY 2021-22 | 2022-03-31 | [6 empty] | No official 31.03.2022 figure located. FY22 + FY23 together added ~1.78 lakh Comp-B pumps (40,000 -> 2,18,539).
FY 2022-23 | 2023-03-31 |  |  | 1519 | 1519 |  |  | Comp-B 2,18,539 as on 31.03.2023 (MNRE report May 2023 via Mongabay; PIB gives 2,08,648 total pumps on 28.02.2023). Comp-C first 1,519 by Jun 2023. Column D = two years (FY22+FY23) combined.
FY 2023-24 | 2024-03-31 | 310000 |  | 8000 |  |  |  | ESTIMATE: 31.01.2024 official = 2,95,823 B / 7,384 C; run-rate ~7,000/month -> ~3.1 lakh B and ~8,000 C by 31.03.2024.
FY 2024-25 | 2025-03-31 | 740000 |  | 260000 |  |  | DfG 2024-25: n/a | ESTIMATE: 31.01.2025 official = 6,69,484 B / 1,92,905 C; 30.06.2025 = 8.4 lakh B / 5.9 lakh C. Interpolated to ~7.4 lakh B and ~2.6 lakh C at 31.03.2025. Secondary sources quote 4.4 lakh B and 2.6 lakh C added in FY25.
FY 2025-26 | 2026-03-31 | 1060000 |  | 1400000 |  |  | A 1,000 MW; B 5,00,000 pumps; C 3,00,000 pumps (Standing Cttee DfG 2025-26) | ESTIMATE: 31.12.2025 = 9,75,227 B / 12,01,552 C; 30.04.2026 = 10,90,815 B / 15,87,009 C; Minister 11 Mar 2026: '>10 lakh B, >13 lakh C'. Interpolated ~10.6 lakh B, ~14 lakh C at 31.03.2026. Comp-B target of 5 lakh missed (~3.2 lakh); Comp-C target of 3 lakh exceeded (~11 lakh, feeder-level).
FY 2026-27 YTD (Apr-Aug 2026) | 2026-08-31 |  |  | 1660000 |  |  | Budget Rs 5,000 cr (BE 2026-27); no physical target published | Comp-B 11,80,474 at Aug 2026 (portal via secondary). Comp-C ~16.6 lakh est. from 28,38,970 total pumps on 31.07.2026 (LS) minus ~11.7 lakh B. Column G = official total 31.07.2026.
Cumulative since launch (31 Jul 2026, official) | 2026-07-31 | [5 empty] | Target: 14 lakh B + 35 lakh C = 49 lakh pumps by 31.03.2026 (extended to 31.03.2027 for sanctioned projects) | 28.39 lakh of 49 lakh pumps = ~58% of the pump target; Comp-B at ~84% of 14 lakh; Comp-C at ~47% of 35 lakh; Comp-A at ~17% of 10,000 MW.
Yellow = derived or interpolated. MNRE publishes cumulative progress 'as on' a date, never a FY-wise installation series; year-end values for FY24, FY25 and FY26 are interpolated between the nearest official datapoints (see KUSUM_Timeline). Comp-C counts pumps covered by feeder-level solarisation (FLS) plus individually solarised pumps (IPS).

## KUSUM_Targets
Target / milestone | Value | Deadline | Set by / stated in | Date | Status as of Sep 2026 | Source URL
Original scheme targets (2019) | A 10,000 MW; B 20 lakh standalone pumps; C 15 lakh grid pumps; 25.75 GW | 2022 | CCEA approval Feb 2019 | 2019-02-19 | Superseded | https://www.pib.gov.in/FactsheetDetails.aspx?Id=148576&reg=48&lang=2
Scale-up (Nov 2020) and extension | A 10,000 MW; B 14 lakh; C 35 lakh (incl. feeder-level); 30.8 GW -> 34.8 GW; outlay Rs 34,422 cr | 31 Mar 2026 (OM 01.08.2022) | MNRE / Dept of Expenditure | 2022-08-01 | Current statutory target; scheme period ended 31.03.2026 for new sanctions | https://mnre.gov.in/en/pradhan-mantri-kisan-urja-suraksha-evam-utthaan-mahabhiyaan-pm-kusum/
Pump target raised to 49 lakh (B+C) | B 14 lakh (7 GW); C-IPS 1.5 lakh (1.12 GW); C-FLS 33.5 lakh (16.75 GW); A 10 GW; total 34.8 GW | 31 Mar 2026 | DoE OM 06.09.2023 (Estimates Cttee para 2.53) | 2023-09-06 | Achieved ~28.4 lakh of 49 lakh pumps by 31 Jul 2026 (LS reply) | https://sansad.in/getFile/lsscommittee/Estimates/18_Estimates_7.pdf?source=loksabhadocs
Annual physical target FY 2025-26 | A 1,000 MW; B 5,00,000 pumps; C 3,00,000 pumps; budget Rs 2,600 cr | 31 Mar 2026 | MNRE to Standing Committee on Energy (DfG 2025-26) | 2025-03-01 | B: ~3.2 lakh added (missed). C: ~11 lakh added via FLS (exceeded). A: ~1,000 MW added (765 -> 1,727 MW by Jun 2026, roughly met). Spend 92% above BE (RE Rs 5,000 cr). | https://sansad.in/getFile/lsscommittee/Energy/18_Energy_5.pdf?source=loksabhadocs
Deadline extension for sanctioned projects | Projects with PPA / NTP / LoA issued by 31 Dec 2025 may complete by 31 Mar 2027 (financial closure 30 Sep 2026 for A and C-FLS; B and C-IPS commissioning by 30 Sep 2026) | 31 Mar 2027 | MNRE OM 28 Mar 2026 | 2026-03-28 | In force. No new sanctions; liabilities to be subsumed in PM-KUSUM 2.0 | https://www.energetica-india.net/news/mnre-extends-pm-kusum-project-completion-deadline-to-march-31-2027
Ministry's own completion expectation | All sanctioned pumps (~13 lakh B) installed 'by year end 2026' | Dec 2026 | MNRE to Committee on Estimates | 2025-08-12 | B at 11.8 lakh of 13.07 lakh sanctioned by Aug 2026; plausible | https://sansad.in/getFile/lsscommittee/Estimates/18_Estimates_7.pdf?source=loksabhadocs
PM-KUSUM 2.0 (successor) | ~Rs 50,000 cr outlay; 10 GW agrivoltaics component; feeder-level focus; EFC cleared Dec 2025 | Not notified | Minister Joshi: 'set to be announced anytime' (9 Sep 2026) | 2026-09-09 | NOT approved by Cabinet as of Sep 2026; no pump target published yet | https://www.downtoearth.org.in/energy/centre-readies-pm-kusum-20-as-focus-shifts-to-feeder-level-solarisation
Budget 2026-27 | Rs 5,000 cr BE (RE 2025-26 Rs 5,000 cr; actual 2024-25 Rs 2,560 cr) | FY 2026-27 | Union Budget 2026-27 (PRS) | 2026-02-01 |  | https://prsindia.org/files/budget/budget_parliament/2026/DfG_Analysis_2026-27-Power.pdf

## KUSUM_State_wise_Jul2025
State/UT | Comp-B sanctioned (nos.) | Comp-B installed (nos.) | Installed as % of sanctioned | Comp-A sanctioned (MW) | Comp-A installed (MW)
Andaman and Nicobar | 34 | 0
Arunachal Pradesh | 700 | 604
Assam | 4000 | 0 |  | 2 | 0
Chhattisgarh |  |  |  | 330 | 7
Goa | 900 | 100 |  | 50 | 0
Gujarat | 18212 | 12016 |  | 500 | 0
Haryana | 197655 | 161073 |  | 158 | 16.61
Himachal Pradesh | 1270 | 959 |  | 100 | 100
Jammu and Kashmir | 5000 | 2955
Jharkhand | 52985 | 36346
Karnataka | 26365 | 2388
Kerala | 8 | 8
Ladakh | 1400 | 0
Madhya Pradesh | 59400 | 7325 |  | 1790 | 52.13
Maharashtra | 555000 | 423379 |  | 260 | 4
Manipur | 450 | 150
Meghalaya | 2735 | 98
Mizoram | 1700 | 40
Nagaland | 265 | 65
Odisha | 16441 | 5713 |  | 90 | 0
Puducherry | 72 | 0
Punjab | 18000 | 15993
Rajasthan | 162914 | 106831 |  | 5250 | 457.25
Tamil Nadu | 5187 | 4260 |  | 14 | 3
Telangana | 20000 | 0 |  | 1450 | 0
Tripura | 11114 | 5082 |  | 5 | 0
Uttar Pradesh | 107266 | 66468 |  | 1 | 1
Uttarakhand | 3685 | 1477
Total
Source: Standing Committee on Energy, 10th Report (Sep 2025), Annexure IV: State-wise progress under PM-KUSUM as on 31.07.2025. Official totals: Comp-B 12,72,758 sanctioned / 8,53,330 installed; Comp-A 10,000 MW sanctioned / 640.99 MW installed. https://sansad.in/getFile/lsscommittee/Energy/18_Energy_10.pdf?source=loksabhadocs